HACKATHON 2025

CodeAura

Codebase Intelligence Agent

PROJECT TASK BOOK & SPRINT PLAN

10-Hour Execution Guide  ·  Team Aura

| MEMBER | ROLE |
| --- | --- |
| ME (You) | Lead Developer — Backend, AI Pipeline, Architecture, Core Logic |
| MPP | Contributor — QA Testing, README, Demo Repos, Gemini API Setup, Pitch Support |
| SKP | Contributor — Frontend UI Styling, React Components, D3 Graph, Animations, Pitch Deck |

Team Aura  ·  Codebase Intelligence Agent  ·  All Rights Reserved

# Document Guide & Legend

This task book is the single source of truth for Team Aura's 10-hour hackathon execution. Every task, time block, owner, and deliverable is listed here. Read this before writing a single line of code.

## Owner Color Key

| BADGE | PERSON | SCOPE OF WORK |
| --- | --- | --- |
| ● ME | You (Lead Dev) | All backend logic, AI integration, AST parsing, RAG pipeline, D3 graph, React architecture, API design, deployment decisions |
| ◆ MPP | MPP (Teammate) | QA testing on demo repos, README writing, demo script rehearsal, Gemini API key setup, .env configuration, output screenshots |
| ■ SKP | SKP (Teammate) | React component building, UI styling, loading animations, D3 graph, tab layout, pitch deck slides |
| ★ ALL | Entire Team | Standup checkpoints, blocker discussions, final demo run-through |

## Priority Key

| 🔴 CRITICAL | Mandatory features (M1, M2, M3). If these don't work, we fail. Non-negotiable. |
| --- | --- |
| 🟠 HIGH | Bonus features (B1, B2, B3) and the Ask AI panel. Major scoring differentiators. |
| 🔵 MEDIUM | UI polish, error handling, loading states — elevates demo quality significantly. |
| ⚪ LOW | Documentation, README, pitch deck — ship only if time permits after HIGH tasks. |

## The Golden Rule

M1 + M2 + M3 must be complete and working before any bonus feature is touched. A polished, complete set of mandatory features outscores a half-built bonus every time.

# Master Sprint Timeline

Every time block below must be completed before the next begins. Check off tasks as they finish. If a block runs over, immediately deprioritize the lowest-priority item in the next block.

| TIME BLOCK | PHASE | ME (Lead) | MPP | SKP |
| --- | --- | --- | --- | --- |
| H0 – H1 | Project Scaffold & Environment | Monorepo setup, Express scaffold, simple-git clone endpoint, folder walk API | Gemini API key config, .env file, test API ping, pull 3 demo repos locally | Vite + React project init, install D3, set up tab layout shell |
| H1 – H3 | M1 + M2 Core Logic | Recursive dir walker, ignore lists, language detection, entry point heuristics, Gemini API call for M1 folder analysis, M2 execution chain builder | Test M1 + M2 on all 3 demo repos, log any broken responses, report bugs to ME | Build FolderTree React component, wire M1 API response to UI, color-code by criticality |
| H3 – H5 | M3 Dependency Graph | AST import extraction (acorn for JS, ast for Python), adjacency list builder, REST endpoint returning graph JSON | Test M3 on express repo, verify node links, screenshot graph output, prepare M3 test notes | Build D3 force-directed graph component, click-to-highlight paths, zoom/pan, connect to M3 API |
| H5 – H7 | RAG Pipeline + Ask AI Panel | Chunk source files (200-token windows), Gemini embeddings, in-memory vector store, cosine similarity search, chat API endpoint | Write 10 test questions for the Ask AI panel across 3 repos, verify answer quality, flag errors | Build Ask AI chat tab UI, message bubbles, loading spinner, wire to backend chat endpoint |
| H7 – H8.5 | Bonus Features + UI Polish | B1 critical file scoring, B2 swimlane execution trace, B3 AI summary card, error handling, loading states, Gemini result caching | Write README (tech stack, setup, usage), capture final screenshots, run full end-to-end test on all 3 demo repos | Polish animations, add progress bar for analysis loading, style B3 summary card, fix any visual bugs from ME feedback |
| H8.5 – H10 | Demo Prep & Submission | GitHub push, final bug fixes, pre-cache demo repos, rehearse demo, handle any last-minute judge's repo test | Final README review, GitHub repo link ready, demo script printed/noted, set up laptop for presentation | Prepare 5-min pitch slides (5 slides max), rehearse talking points, time the presentation |

# Detailed Task Breakdown

Each task card below contains a full description, subtask list with owner assignments, and a clear deliverable checkpoint. Complete subtasks in order.

| TASK 01 · Project Scaffold & Environment Setup | ⏱ H0:00 – H1:00 | ● ME (Lead) | CRITICAL |
| --- | --- | --- | --- |

PHASE: Phase 1 — Bootstrap     DESCRIPTION: Set up the full monorepo structure, install all dependencies, and verify the core pipeline (GitHub URL → clone → folder list) works end-to-end before any feature work begins.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Create monorepo: /backend and /frontend folders, shared package.json root | ● ME (Lead) | [ ] Pending |
| 2. | Backend: npm init, install express, cors, simple-git, acorn, dotenv | ● ME (Lead) | [ ] Pending |
| 3. | Write /api/clone endpoint: accepts GitHub URL, clones to /tmp/sandbox/{id} | ● ME (Lead) | [ ] Pending |
| 4. | Write /api/files endpoint: walks cloned repo, returns file tree JSON (ignore node_modules, .git, dist) | ● ME (Lead) | [ ] Pending |
| 5. | Test clone + walk pipeline on expressjs/express — confirm JSON response | ● ME (Lead) | [ ] Pending |
| 6. | Frontend: npx create vite@latest, install axios, react-router, d3, tailwindcss | ■ SKP | [ ] Pending |
| 7. | Build shell layout: Topbar (URL input + Analyse button), 4-tab navigation bar (M1/M2/M3/Ask AI) | ■ SKP | [ ] Pending |
| 8. | Placeholder panels for all 4 tabs — just empty divs with tab titles for now | ■ SKP | [ ] Pending |
| 9. | Create .env file: GEMINI_API_KEY, PORT=4000, SANDBOX_PATH=/tmp/sandbox | ◆ MPP | [ ] Pending |
| 10. | Confirm Gemini API key is active — ping with a test 'Hello' request, screenshot response | ◆ MPP | [ ] Pending |
| 11. | Pull 3 demo repos locally: expressjs/express, tiangolo/fastapi, gothinkster/realworld | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: Working GitHub URL → folder tree JSON pipeline. Frontend shell renders with 4 tabs. Gemini API confirmed active.

| TASK 02 · M1 — Folder Structure Analysis | ⏱ H1:00 – H2:00 | ● ME (Lead) | CRITICAL |
| --- | --- | --- | --- |

PHASE: Phase 2 — Mandatory Features     DESCRIPTION: Build the M1 analysis engine: recursively map the folder hierarchy, send clusters to Gemini for plain-English explanations, and return a structured JSON with criticality scores for each directory.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Build analyzeStructure(repoPath): returns array of {path, type, fileCount, depth} | ● ME (Lead) | [ ] Pending |
| 2. | Implement criticality scorer: count files + detect keywords (controller, auth, db, config, route, service, model) | ● ME (Lead) | [ ] Pending |
| 3. | Write Gemini prompt for folder analysis: batch top-level dirs, request purpose + one-line description per folder | ● ME (Lead) | [ ] Pending |
| 4. | Create /api/analyze/structure endpoint: accepts repo session ID, returns enriched folder JSON | ● ME (Lead) | [ ] Pending |
| 5. | Handle edge cases: empty repos, single-file repos, repos with no src/ folder | ● ME (Lead) | [ ] Pending |
| 6. | Build FolderTree component: tree view with expand/collapse, color badge by criticality (red/amber/blue/gray) | ■ SKP | [ ] Pending |
| 7. | Add hover tooltip on each folder showing the Gemini description | ■ SKP | [ ] Pending |
| 8. | Wire M1 tab to call /api/analyze/structure and render FolderTree with real data | ■ SKP | [ ] Pending |
| 9. | Test M1 on all 3 demo repos, verify folder descriptions make sense, paste any broken outputs to ME | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: M1 tab fully functional: folder tree renders with Gemini explanations and criticality color coding for all 3 demo repos.

| TASK 03 · M2 — Entry Point Detection & Execution Flow | ⏱ H2:00 – H3:00 | ● ME (Lead) | CRITICAL |
| --- | --- | --- | --- |

PHASE: Phase 2 — Mandatory Features     DESCRIPTION: Detect the project's entry point through file-name heuristics and package.json inspection, then trace the initial execution chain by following imports from the entry file, building a readable execution timeline.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Build detectEntryPoint(repoPath): check package.json main/scripts.start, then scan for server.js, main.py, index.js, app.py, manage.py, Program.cs | ● ME (Lead) | [ ] Pending |
| 2. | Build traceExecutionChain(entryFile, repoPath): follow top-level imports recursively up to depth 4, return ordered array of {file, action, connects_to} | ● ME (Lead) | [ ] Pending |
| 3. | Write Gemini prompt: given entry file + first 50 lines, describe what each step does in plain English | ● ME (Lead) | [ ] Pending |
| 4. | Create /api/analyze/entrypoint endpoint returning {entryFile, language, executionChain[]} | ● ME (Lead) | [ ] Pending |
| 5. | Build ExecutionFlow component: vertical timeline, each step as a card with file name + description, animated entry on load | ■ SKP | [ ] Pending |
| 6. | Add a highlighted badge on the detected entry file showing language (Node.js / Python / Java / React App) | ■ SKP | [ ] Pending |
| 7. | Wire M2 tab: call entrypoint API, render ExecutionFlow timeline with real data | ■ SKP | [ ] Pending |
| 8. | Test M2 on all 3 demo repos, verify entry file is detected correctly, record any misdetections | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: M2 tab fully functional: entry file detected, execution chain renders as animated timeline for all 3 demo repos.

| TASK 04 · M3 — Dependency Mapping with D3 Graph | ⏱ H3:00 – H5:00 | ● ME (Lead) | CRITICAL |
| --- | --- | --- | --- |

PHASE: Phase 2 — Mandatory Features     DESCRIPTION: Build the AST-based import extraction engine for JS and Python, construct a directed dependency graph, expose it via API, and render it as an interactive D3.js force-directed graph on the frontend. This is the most complex task — allocate the full 2 hours.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Build extractImportsJS(filePath): use acorn to parse ES modules and CommonJS require(), return array of resolved file paths | ● ME (Lead) | [ ] Pending |
| 2. | Build extractImportsPython(filePath): use regex on import/from statements, resolve relative imports to absolute repo paths | ● ME (Lead) | [ ] Pending |
| 3. | Build buildDependencyGraph(repoPath): walk all source files, call extractImports per file, construct {nodes: [], edges: []} adjacency structure | ● ME (Lead) | [ ] Pending |
| 4. | Score each node: importedByCount = number of files that import this file (higher = more critical) | ● ME (Lead) | [ ] Pending |
| 5. | Cap at top 100 nodes for large repos (filter by importedByCount descending) | ● ME (Lead) | [ ] Pending |
| 6. | Create /api/analyze/dependencies endpoint returning graph JSON with nodes + edges | ● ME (Lead) | [ ] Pending |
| 7. | Handle multi-language repos: detect language per file by extension, route to correct extractor | ● ME (Lead) | [ ] Pending |
| 8. | Build D3ForceGraph React component: force-directed layout, nodes sized by importedByCount, colored by module type (route/controller/service/model/other) | ■ SKP | [ ] Pending |
| 9. | Add click interaction: clicking a node highlights all directly connected nodes and grays out the rest | ■ SKP | [ ] Pending |
| 10. | Add zoom/pan with d3.zoom(), add a Reset View button | ■ SKP | [ ] Pending |
| 11. | Add a legend card: circle sizes = importance, colors = module type | ■ SKP | [ ] Pending |
| 12. | Wire M3 tab: call dependencies API, pass JSON to D3ForceGraph, render with loading skeleton | ■ SKP | [ ] Pending |
| 13. | Test M3 graph on expressjs/express — verify at least 15 nodes and correct connections visible | ◆ MPP | [ ] Pending |
| 14. | Test M3 on fastapi repo — verify Python imports parse correctly | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: M3 tab fully functional: interactive D3 dependency graph renders, click-to-highlight works, legend visible. Both JS and Python repos work.

| TASK 05 · Ask AI — Conversational RAG Panel (Creative Differentiator) | ⏱ H5:00 – H7:00 | ● ME (Lead) | HIGH |
| --- | --- | --- | --- |

PHASE: Phase 3 — Differentiator Feature     DESCRIPTION: Build the RAG (Retrieval-Augmented Generation) pipeline that enables natural language Q&A over the codebase. This is the hackathon differentiator — the feature no other team will ship. It chunks all source files, embeds them with Gemini, stores vectors in memory, and retrieves relevant context for each user question.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Build chunkCodebase(repoPath): read all source files, split into ~200 token chunks with file path metadata | ● ME (Lead) | [ ] Pending |
| 2. | Build embedChunks(chunks): call Gemini text-embedding-004 API, store [{chunk, embedding, filePath}] in memory array | ● ME (Lead) | [ ] Pending |
| 3. | Build semanticSearch(query, chunks, topK=5): cosine similarity between query embedding and all chunk embeddings, return top 5 | ● ME (Lead) | [ ] Pending |
| 4. | Build Gemini RAG prompt: system = 'You are a senior dev explaining this codebase', context = top 5 chunks, user = question | ● ME (Lead) | [ ] Pending |
| 5. | Create /api/chat endpoint: POST {sessionId, message} → embed query → retrieve chunks → Gemini answer → return text | ● ME (Lead) | [ ] Pending |
| 6. | Cap codebase at 500 files for RAG to avoid token overflow — sort by importedByCount to keep most important files | ● ME (Lead) | [ ] Pending |
| 7. | Build AskAI chat tab UI: message list (user right, AI left), text input, Send button, typing indicator dots | ■ SKP | [ ] Pending |
| 8. | Add suggested question chips below input: 'Where is auth handled?', 'What is the entry point?', 'Which file handles DB connections?' | ■ SKP | [ ] Pending |
| 9. | Wire Ask AI tab: POST to /api/chat, append AI response to message list with smooth scroll | ■ SKP | [ ] Pending |
| 10. | Write 10 test questions and run them on expressjs/express, document answer quality (pass/fail) | ◆ MPP | [ ] Pending |
| 11. | Test edge case: ask a question about a file that doesn't exist, verify graceful response | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: Ask AI tab functional: type a question about the repo, get a Gemini-powered answer with file references in under 10 seconds.

| TASK 06 · B1 — Critical File Identification | ⏱ H7:00 – H7:40 | ● ME (Lead) | HIGH |
| --- | --- | --- | --- |

PHASE: Phase 4 — Bonus Features     DESCRIPTION: Score every file by import frequency and keyword density, then surface the top 5 most critical files with color-coded risk badges. This makes the analysis visually dramatic and instantly convincing to judges.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Build scoreCriticalFiles(graph, repoPath): score = (importedByCount * 3) + (keywordScore * 2) where keywords = [auth, db, config, router, middleware, model] | ● ME (Lead) | [ ] Pending |
| 2. | Return top 5 files with score, reasons array, and category (auth / database / routing / business-logic / config) | ● ME (Lead) | [ ] Pending |
| 3. | Create /api/analyze/critical endpoint returning sorted top-5 critical files | ● ME (Lead) | [ ] Pending |
| 4. | Build CriticalFiles sidebar component: ranked list with #1–#5, red/amber/blue score badges, file name, and reason chips | ■ SKP | [ ] Pending |
| 5. | Add CriticalFiles panel to M1 tab as a right-side summary column | ■ SKP | [ ] Pending |
| 6. | Test on gothinkster/realworld — verify auth and DB config files rank in top 3 | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: Critical Files panel visible in M1 tab: top 5 files ranked with category badges and justification text.

| TASK 07 · B3 — AI Repository Summary Card | ⏱ H7:40 – H8:20 | ● ME (Lead) | HIGH |
| --- | --- | --- | --- |

PHASE: Phase 4 — Bonus Features     DESCRIPTION: Generate a high-level repository summary using a single Gemini call with the folder structure, entry point, and top files as context. Display it as a hero card on the dashboard — the first thing judges see when analysis completes.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Build generateSummary(folderData, entryPoint, criticalFiles): construct a rich Gemini prompt requesting tech stack, architecture style, key design patterns, quality assessment | ● ME (Lead) | [ ] Pending |
| 2. | Parse Gemini response into: {techStack[], architectureStyle, designPatterns[], qualitySignals[], oneLineSummary} | ● ME (Lead) | [ ] Pending |
| 3. | Create /api/analyze/summary endpoint | ● ME (Lead) | [ ] Pending |
| 4. | Build SummaryCard component: dark header with repo name, one-line AI summary, tech stack pills, architecture style badge, quality signal chips | ■ SKP | [ ] Pending |
| 5. | Add SummaryCard as the hero section above the tabs — first thing visible after analysis completes | ■ SKP | [ ] Pending |
| 6. | Test summary quality on all 3 demo repos, flag any hallucinations or wrong tech stacks | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: AI Summary hero card renders above tabs after analysis: shows tech stack, architecture style, and quality signals.

| TASK 08 · UI Polish, Loading States & Error Handling | ⏱ H7:00 – H8:20 | ■ SKP | MEDIUM |
| --- | --- | --- | --- |

PHASE: Phase 4 — Polish     DESCRIPTION: While ME builds bonus features, SKP polishes the UI to demo-ready quality. Loading states, smooth animations, and error boundaries are the difference between a prototype and a product.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Add full-page loading overlay: animated hexagon spinner + 'Analysing repository...' text with progress steps | ■ SKP | [ ] Pending |
| 2. | Add per-tab skeleton loaders: gray placeholder cards that animate while each analysis section loads | ■ SKP | [ ] Pending |
| 3. | Add progress bar to the Analyse button showing 5 steps: Cloning → Walking → M1 → M2 → M3 → Ready | ■ SKP | [ ] Pending |
| 4. | Add error boundary for each tab: if an API call fails, show a friendly 'Analysis failed — try another repo' card instead of crash | ■ SKP | [ ] Pending |
| 5. | Polish topbar: add CodeAura logo/icon, show analysed repo URL as a clickable link after analysis | ■ SKP | [ ] Pending |
| 6. | Responsive check: verify dashboard looks clean on a 13-inch laptop screen (1280×800) | ■ SKP | [ ] Pending |
| 7. | Add smooth fade-in animation on each tab panel when it receives data | ■ SKP | [ ] Pending |

✓ DELIVERABLE: Dashboard has professional loading states, error handling, and smooth animations. Looks polished at demo resolution.

| TASK 09 · README & Project Documentation | ⏱ H7:30 – H8:30 | ◆ MPP | LOW |
| --- | --- | --- | --- |

PHASE: Phase 4 — Documentation     DESCRIPTION: Write the GitHub README that judges and evaluators will read. Must be scannable, professional, and show the project clearly. Use the solution document from earlier as the reference for content.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Write README header: CodeAura logo text, one-line tagline, badges (Node.js, Gemini AI, React) | ◆ MPP | [ ] Pending |
| 2. | Write Problem Statement section: 3-4 lines max, reference the 40K line codebase scenario | ◆ MPP | [ ] Pending |
| 3. | Write Features section: M1, M2, M3 as checkboxes, bonus features (B1, B3, Ask AI) as bonus checkboxes | ◆ MPP | [ ] Pending |
| 4. | Write Setup instructions: Prerequisites (Node 18+, Gemini API key), clone repo, npm install, add .env, npm run dev | ◆ MPP | [ ] Pending |
| 5. | Write Usage section: paste GitHub URL, click Analyse, describe each tab in 1-2 lines | ◆ MPP | [ ] Pending |
| 6. | Write Tech Stack section: list backend (Node/Express, Gemini, acorn) and frontend (React, D3, Vite) | ◆ MPP | [ ] Pending |
| 7. | Add screenshots folder, paste final screenshots of M1/M2/M3/Ask AI tabs into README | ◆ MPP | [ ] Pending |
| 8. | Add Team Aura credit line at bottom | ◆ MPP | [ ] Pending |

✓ DELIVERABLE: Complete README.md committed to repo covering setup, features, screenshots, and tech stack.

| TASK 10 · Gemini Result Caching & Performance | ⏱ H8:00 – H8:30 | ● ME (Lead) | MEDIUM |
| --- | --- | --- | --- |

PHASE: Phase 4 — Resilience     DESCRIPTION: Cache all Gemini API responses per session to prevent rate limit hits during the demo. This is a 30-minute insurance task — do it before the demo, not after a failure.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Add in-memory cache: Map<sessionId, {structure, entrypoint, deps, summary}> on the backend | ● ME (Lead) | [ ] Pending |
| 2. | Check cache before any Gemini call — return cached result instantly if available | ● ME (Lead) | [ ] Pending |
| 3. | Pre-warm cache: add a /api/preload endpoint that runs analysis on all 3 demo repos at server startup | ● ME (Lead) | [ ] Pending |
| 4. | Add cache-hit indicator in API response: {cached: true} — SKP can show a 'cached' badge in the UI | ● ME (Lead) | [ ] Pending |
| 5. | Limit analysis to repos under 5000 files: return friendly error message for oversized repos | ● ME (Lead) | [ ] Pending |

✓ DELIVERABLE: All 3 demo repos are pre-cached. Re-analysis returns instantly from cache. Rate limit risk eliminated for demo.

| TASK 11 · Pitch Deck Preparation | ⏱ H8:30 – H9:15 | ■ SKP | MEDIUM |
| --- | --- | --- | --- |

PHASE: Phase 5 — Demo Prep     DESCRIPTION: Build the 5-slide pitch deck. Keep it punchy — judges have heard 15 pitches by the time they see ours. Every slide must earn its place.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Slide 1 — Hook: '40,000 lines. No docs. Day one.' Large text, no bullet points. Team Aura + CodeAura logo. | ■ SKP | [ ] Pending |
| 2. | Slide 2 — Solution: One-line description + architecture diagram (M1/M2/M3/RAG flow). Use the image from our solution doc. | ■ SKP | [ ] Pending |
| 3. | Slide 3 — Live Demo Placeholder: Just says 'LIVE DEMO' in large text. Used during presentation transition. | ■ SKP | [ ] Pending |
| 4. | Slide 4 — Differentiator: 'Ask The Codebase' — screenshot of the Ask AI chat panel. One-liner: No other team ships this. | ■ SKP | [ ] Pending |
| 5. | Slide 5 — Tech Stack + Team: Logo grid (Node, React, Gemini, D3), team names, GitHub repo QR code. | ■ SKP | [ ] Pending |
| 6. | Time the presentation: Slide 1 = 30s, Slide 2 = 30s, Demo = 3 min, Slide 4 = 30s, Slide 5 = 30s. Total = 5 min. | ■ SKP | [ ] Pending |

✓ DELIVERABLE: 5-slide pitch deck complete. Timed at exactly 5 minutes. Exported as PDF backup.

| TASK 12 · Final Testing, GitHub Submission & Demo Rehearsal | ⏱ H9:15 – H10:00 | ★ ALL | CRITICAL |
| --- | --- | --- | --- |

PHASE: Phase 5 — Ship It     DESCRIPTION: Full end-to-end run. Test against an unseen repo to simulate the judge's test. Rehearse the 5-minute pitch twice. Git push everything. Do not write new code after H9:30 — only bug fixes.

| # | SUBTASK | OWNER | STATUS |
| --- | --- | --- | --- |
| 1. | Run full analysis on all 3 pre-chosen demo repos — verify M1, M2, M3, Ask AI all render correctly | ● ME (Lead) | [ ] Pending |
| 2. | Test on one UNSEEN repo (suggestion: pallets/flask on GitHub) — simulate judge test condition | ● ME (Lead) | [ ] Pending |
| 3. | Fix any critical bugs found in unseen repo test — max 20 min budget for this | ● ME (Lead) | [ ] Pending |
| 4. | git add . && git commit -m 'Final submission — CodeAura by Team Aura' && git push | ● ME (Lead) | [ ] Pending |
| 5. | Run pitch rehearsal #1 — all three members present their section, time it | ★ ALL | [ ] Pending |
| 6. | Run pitch rehearsal #2 — fix any stumbles, re-time | ★ ALL | [ ] Pending |
| 7. | Set up presentation laptop: browser open at CodeAura, demo tab pre-loaded with expressjs/express result (cached) | ■ SKP | [ ] Pending |
| 8. | Have GitHub repo URL printed/noted for judges, README URL ready to share | ◆ MPP | [ ] Pending |
| 9. | Verify slides display correctly on presentation screen (check font sizes at distance) | ■ SKP | [ ] Pending |
| 10. | Team sync: agree on who handles judge Q&A for which sections (ME = technical, SKP = UI/UX, MPP = overall pitch) | ★ ALL | [ ] Pending |

✓ DELIVERABLE: Code frozen. Repo submitted to GitHub. Demo laptop ready. Team rehearsed. Confident and prepared.

# Hackathon Day Checklist

Print this page. Check off items in real-time. If you miss a checkpoint by 15+ minutes, immediately re-evaluate the current task — do not let one block cascade.

| ✓ | CHECKPOINT | OWNER | BY |
| --- | --- | --- | --- |
| ☐ | Monorepo scaffold created, all dependencies installed | ● ME (Lead) | H0:45 |
| ☐ | Vite + React frontend shell with 4 tabs renders in browser | ■ SKP | H0:50 |
| ☐ | Gemini API key verified — test ping successful | ◆ MPP | H0:30 |
| ☐ | GitHub URL → clone → file tree JSON works end-to-end | ● ME (Lead) | H1:00 |
| ☐ | M1: Folder tree renders with Gemini descriptions in UI | ● ME (Lead) | H2:00 |
| ☐ | M1: Criticality color badges working (red/amber/blue/gray) | ■ SKP | H2:00 |
| ☐ | M2: Entry point detected correctly for all 3 demo repos | ● ME (Lead) | H3:00 |
| ☐ | M2: Execution flow timeline animates in the UI | ■ SKP | H3:00 |
| ☐ | M3: Dependency graph JSON returned from API (JS repo) | ● ME (Lead) | H4:30 |
| ☐ | M3: D3 force graph renders and click-to-highlight works | ■ SKP | H5:00 |
| ☐ | M3: Python repo dependency extraction works (fastapi test) | ◆ MPP | H5:00 |
| ☐ | Ask AI: RAG pipeline embeds codebase and returns answers | ● ME (Lead) | H6:30 |
| ☐ | Ask AI: Chat UI sends questions and displays responses | ■ SKP | H7:00 |
| ☐ | B1: Critical files panel shows top 5 ranked files | ● ME (Lead) | H7:40 |
| ☐ | B3: AI Summary hero card renders above tabs | ● ME (Lead) | H8:20 |
| ☐ | All 3 demo repos pre-cached — instant reload confirmed | ● ME (Lead) | H8:30 |
| ☐ | Loading states and error boundaries working in all tabs | ■ SKP | H8:20 |
| ☐ | README complete with screenshots, setup, and features list | ◆ MPP | H8:30 |
| ☐ | Pitch deck complete — 5 slides, timed at 5 minutes | ■ SKP | H9:15 |
| ☐ | Unseen repo test (flask) — M1/M2/M3 all produce output | ● ME (Lead) | H9:30 |
| ☐ | Git push: final submission commit pushed to GitHub | ● ME (Lead) | H9:30 |
| ☐ | Pitch rehearsal #1 complete — all team members practiced | ★ ALL | H9:45 |
| ☐ | Pitch rehearsal #2 complete — timing confirmed at 5 min | ★ ALL | H10:00 |
| ☐ | Presentation laptop set up, demo pre-loaded and cached | ■ SKP | H10:00 |

If you complete all checkpoints by H9:30, you are on track for a top-tier submission.